## TC_Home
Test Case ID |  | TC_Home | Test Case Description | Testing navigations in Ebuy Online Shopping home page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate home page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'login' on the ribbon and enter credentials |  | Navigate to the home page | As Expected |  |  | Pass
2 | Select 'signup' on the ribbon and enter credentials |  | Navigate to the login page | As Expected |  |  | Pass
3 | Select 'home' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
5 | Select 'categories' button from the home page |  | Navigate to the product list page. | As Expected |  |  | Pass

## TC_Cart_list
Test Case ID |  | TC_Cart_list | Test Case Description | Testing navigations in Ebuy Online Shopping home page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate cart page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'login' on the ribbon and enter credentials |  | Navigate to the home page | As Expected |  |  | Pass
2 | Select 'signup' on the ribbon and enter credentials |  | Navigate to the login page | As Expected |  |  | Pass
3 | Select 'store' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
4 | Select 'cart' on the ribbon |  | Navigate to the cart page | As Expected |  |  | Pass
5 | Select 'home' in the cart page |  | Navigate to the home page | As Expected |  |  | Pass
6 | Select 'checkout' in the cart page |  | Navigate to the order summary page | As Expected |  |  | Pass

## TC_Summary_list
Test Case ID |  | TC_Summary_list | Test Case Description | Testing navigations in Ebuy Online Shopping home page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate order summary page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'login' on the ribbon and enter credentials |  | Navigate to the home page | As Expected |  |  | Pass
2 | Select 'signup' on the ribbon and enter credentials |  | Navigate to the login page | As Expected |  |  | Pass
3 | Select 'home' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
5 | Select 'cart' on the ribbon |  | Navigate to the cart page | As Expected |  |  | Pass
7 | Select 'back to cart' in order summary page |  | Navigate to the cart page | As Expected |  |  | Pass

## TC_Checkout
Test Case ID |  | TC_Summary_list | Test Case Description | Testing navigations in Ebuy Online Shopping home page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate order summary page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'login' on the ribbon and enter credentials |  | Navigate to the home page | As Expected |  |  | Pass
2 | Select 'signup' on the ribbon and enter credentials |  | Navigate to the login page | As Expected |  |  | Pass
3 | Select 'home' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
5 | Select 'cart' on the ribbon |  | Navigate to the cart page | As Expected |  |  | Pass
7 | Select 'back to cart' in order summary page |  | Navigate to the cart page | As Expected |  |  | Pass
1 | Select 'login' icon from the navigation bar and enter credentials |  | Navigation to home page | As expected |  |  | Pass
2 | Select 'Add to cart' icon from the home page |  | Selected product will be added to the cart | As expected |  |  | Pass
3 | Select 'cart' icon on the navigation bar |  | Navigation to the cart_list page | As expected |  |  | Pass
4 | Select continue shopping button |  | Navigation to home page | As expected |  |  | Pass
5 | Select increment/decrement icon on the cart_list page |  | Selected items count should increase or decrease accordingly | As expected |  |  | Pass
6 | Select checkout button on the cart_list page |  | Navigation to the checkout page where order summary and shipping information is displayed | As expected |  |  | Pass
7 | Enter address field in the shipping information |  | User should be able to enter the address field | As expected |  |  | Pass
8 | Enter details of city field in the shipping information |  | User should be able to enter the details of the city | As expected |  |  | Pass
9 | Enter the details of the State field in the shipping information |  | User should be able to enter the details of the state | As expected |  |  | Pass
10 | Enter the details of Zip code in the shipping information |  | User should be able to enter details of the zip code | As expected |  |  | Pass
11 | Select continue button on the shipping information |  | Payment options (paypal, debit and credit) will be displayed | As expected |  |  | Pass
12 | Select 'back to cart' on order summary tab |  | Navigation to the cart_list page | As expected |  |  | Pass

## TC_Admin_list
Test Case ID |  | TC_Admin_list | Test Case Description | Testing navigations for Admin page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate Admin page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'Django administration' and enter credentials |  | Navigate to the admin home page | As Expected |  |  | Pass
2 | Select 'view site' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
3 | Select 'change password' on the ribbon |  | Navigate to the password change page | As Expected |  |  | Pass
4 | Select 'logout' on the ribbon |  | Navigate to the admin login page | As Expected |  |  | Pass
5 | Select 'authentication and authorization' under site administration |  | Navigate to the authentication and authorization page | As Expected |  |  | Pass
6 | Select 'groups' under authentication and authorization |  | Navigate to the group page | As Expected |  |  | Pass
7 | Select 'users' under authentication and authorization |  | Navigate to the users page | As Expected |  |  | Pass
8 | Select 'store' under site administration |  | Navigate to the store administration page | As Expected |  |  | Pass
9 | Select 'customers' under store |  | Navigate to the customer page | As Expected |  |  | Pass
10 | Select 'order items' under store |  | Navigate to the order item page | As Expected |  |  | Pass
11 | Select 'orders' under store |  | Navigate to the order page | As Expected |  |  | Pass
12 | Select 'products' under store |  | Navigate to the product page | As Expected |  |  | Pass
13 | Select 'shipping address' under store |  | Navigate to the shipping address page | As Expected |  |  | Pass

## TC_Admin_Store_list
Test Case ID |  | TC_Store_list | Test Case Description | Testing navigations for store administration page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate Store administration page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'Django administration' and enter credentials |  | Navigate to the admin home page | As Expected |  |  | Pass
2 | Select 'view site' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
3 | Select 'change password' on the ribbon |  | Navigate to the password change page | As Expected |  |  | Pass
4 | Select 'logout' on the ribbon |  | Navigate to the admin login page | As Expected |  |  | Pass
8 | Select 'store' under site administration |  | Navigate to the store administration page | As Expected |  |  | Pass
9 | Select 'customers' under store |  | Navigate to the customer page | As Expected |  |  | Pass
10 | Select 'order items' under store |  | Navigate to the order item page | As Expected |  |  | Pass
11 | Select 'orders' under store |  | Navigate to the order page | As Expected |  |  | Pass
12 | Select 'products' under store |  | Navigate to the product page | As Expected |  |  | Pass
13 | Select 'shipping address' under store |  | Navigate to the shipping address page | As Expected |  |  | Pass

## TC_Admin_Customers_list
Test Case ID |  | TC_Customers_list | Test Case Description | Testing navigations for customer page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate customer page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'Django administration' and enter credentials |  | Navigate to the admin home page | As Expected |  |  | Pass
2 | Select 'view site' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
3 | Select 'change password' on the ribbon |  | Navigate to the password change page | As Expected |  |  | Pass
4 | Select 'logout' on the ribbon |  | Navigate to the admin login page | As Expected |  |  | Pass
5 | Select 'authentication and authorization' under site administration |  | Navigate to the authentication and authorization page | As Expected |  |  | Pass
6 | Select 'groups' under authentication and authorization |  | Navigate to the group page | As Expected |  |  | Pass
7 | Select 'users' under authentication and authorization |  | Navigate to the users page | As Expected |  |  | Pass
8 | Select 'store' under site administration |  | Navigate to the store administration page | As Expected |  |  | Pass
9 | Select 'customers' under store |  | Navigate to the customer page | As Expected |  |  | Pass
10 | Select 'order items' under store |  | Navigate to the order item page | As Expected |  |  | Pass
11 | Select 'orders' under store |  | Navigate to the order page | As Expected |  |  | Pass
12 | Select 'products' under store |  | Navigate to the product page | As Expected |  |  | Pass
13 | Select 'shipping address' under store |  | Navigate to the shipping address page | As Expected |  |  | Pass
14 | Select 'customer name' under customer |  | Navigate to the change customer page | As Expected |  |  | Pass
15 | Select 'add customer' on the customer page |  | Navigate to the add customer page | As Expected |  |  | Pass

## TC_Admin_Shipping address_list
Test Case ID |  | TC_Shipping address_list | Test Case Description | Testing navigations for shipping address page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Raviprakash | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate shipping address page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'Django administration' and enter credentials |  | Navigate to the admin home page | As Expected |  |  | Pass
2 | Select 'view site' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
3 | Select 'change password' on the ribbon |  | Navigate to the password change page | As Expected |  |  | Pass
4 | Select 'logout' on the ribbon |  | Navigate to the admin login page | As Expected |  |  | Pass
5 | Select 'authentication and authorization' under site administration |  | Navigate to the authentication and authorization page | As Expected |  |  | Pass
6 | Select 'groups' under authentication and authorization |  | Navigate to the group page | As Expected |  |  | Pass
7 | Select 'users' under authentication and authorization |  | Navigate to the users page | As Expected |  |  | Pass
8 | Select 'store' under site administration |  | Navigate to the store administration page | As Expected |  |  | Pass
9 | Select 'customers' under store |  | Navigate to the customer page | As Expected |  |  | Pass
10 | Select 'order items' under store |  | Navigate to the order item page | As Expected |  |  | Pass
11 | Select 'orders' under store |  | Navigate to the order page | As Expected |  |  | Pass
12 | Select 'products' under store |  | Navigate to the product page | As Expected |  |  | Pass
13 | Select 'shipping address' under store |  | Navigate to the shipping address page | As Expected |  |  | Pass
15 | Select 'add shipping address' on the shipping address page |  | Navigate to the add shipping address | As Expected |  |  | Pass

## TC_Admin_OrderItems_list
Test Case ID |  | TC_OrderItems_list | Test Case Description | Testing navigations for order items page
Created By |  | Kavya Raviprakash | Reviewed By | Shirish |  | Version |  | 1
QA Tester’s Log |  | All functionalities are working as expected.
Tester's Name |  | Kavya Ravi | Date Tested | 2021-08-01 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data Requirement
1 | Having a device with proper internet connection |  |  | 1 | Application working link
2 | Able to login to the page |  |  | 2
3 | Ebuy Shopping Site |  |  | 3
Test Conditions |  | Validate order items page
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Select 'Django administration' and enter credentials |  | Navigate to the admin home page | As Expected |  |  | Pass
2 | Select 'view site' on the ribbon |  | Navigate to the home page | As Expected |  |  | Pass
3 | Select 'change password' on the ribbon |  | Navigate to the password change page | As Expected |  |  | Pass
4 | Select 'logout' on the ribbon |  | Navigate to the admin login page | As Expected |  |  | Pass
5 | Select 'authentication and authorization' under site administration |  | Navigate to the authentication and authorization page | As Expected |  |  | Pass
6 | Select 'groups' under authentication and authorization |  | Navigate to the group page | As Expected |  |  | Pass
7 | Select 'users' under authentication and authorization |  | Navigate to the users page | As Expected |  |  | Pass
8 | Select 'store' under site administration |  | Navigate to the store administration page | As Expected |  |  | Pass
9 | Select 'customers' under store |  | Navigate to the customer page | As Expected |  |  | Pass
10 | Select 'order items' under store |  | Navigate to the order item page | As Expected |  |  | Pass
11 | Select 'orders' under store |  | Navigate to the order page | As Expected |  |  | Pass
12 | Select 'products' under store |  | Navigate to the product page | As Expected |  |  | Pass
13 | Select 'shipping address' under store |  | Navigate to the shipping address page | As Expected |  |  | Pass
14 | Select 'orderitem object' under order item |  | Navigate to the change order item page | As Expected |  |  | Pass
15 | Select 'add order item' on the customer page |  | Navigate to the add order itempage | As Expected |  |  | Pass