## Burndown of Entire Project
Story/Task No. | Estimated Hours | Swetha | Kavya | Vahini | Hannah | Actual Hours | Date Started | Date Completed | Actual Hours left | Estimated Hours Left
0.1.1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2020-09-08 | 2020-09-10 | 221.4 | 213.89
0.1.2 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2020-09-08 | 2020-09-10 | 219.4 | 212.89
0.1.3 | 1 | 0.5 | 0.25 | 0.25 | 0.25 | 1.25 | 2020-09-08 | 2020-09-10 | 218.15 | 211.89
0.1.4 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 2020-09-08 | 2020-09-10 | 217.15 | 210.89
0.1.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.25 | 1.75 | 2020-09-08 | 2020-09-10 | 215.4 | 209.39
0.1.6 | 0.5 | 0.25 | 0.25 | 0.25 |  | 0.75 | 2020-09-08 | 2020-09-10 | 214.65 | 208.89
0.2.1 | 2 | 1 |  | 0.5 | 0.25 | 1.75 | 2020-09-08 | 2020-09-12 | 212.9 | 206.89
0.2.2 | 0.5 | 0.25 |  | 0.05 |  | 0.3 | 2020-09-08 | 2020-09-12 | 212.6 | 206.39
0.2.3 | 1 | 1 |  | 0.25 |  | 1.25 | 2020-09-08 | 2020-09-12 | 211.35 | 205.39
0.2.4 | 1.5 | 0.15 |  | 0.25 | 1 | 1.4 | 2020-09-08 | 2020-09-12 | 209.95 | 203.89
0.3.1 | 0.4 |  |  | 0.25 | 0.25 | 0.5 | 2020-09-08 | 2020-09-14 | 209.45 | 203.49
0.3.2 | 0.4 | 0.05 | 0.05 | 0.25 | 0.25 | 0.6 | 2020-09-08 | 2020-09-14 | 208.85 | 203.09
0.3.3 | 0.4 |  | 0.5 | 0.5 | 0.5 | 1.5 | 2020-09-08 | 2020-09-14 | 207.35 | 202.69
0.3.4 | 0.4 |  |  | 0.5 |  | 0.5 | 2020-09-08 | 2020-09-14 | 206.85 | 202.29
0.3.5 | 0.4 |  |  |  | 0.5 | 0.5 | 2020-09-08 | 2020-09-14 | 206.35 | 201.89
0.3.6 | 0.4 |  |  |  | 0.5 | 0.5 | 2020-09-08 | 2020-09-14 | 205.85 | 201.49
0.3.7 | 0.4 |  |  | 0.5 |  | 0.5 | 2020-09-08 | 2020-09-14 | 205.35 | 201.09
0.3.8 | 0.4 |  |  |  | 0.5 | 0.5 | 2020-09-08 | 2020-09-14 | 204.85 | 200.69
0.3.9 | 0.4 |  |  |  | 0.5 | 0.5 | 2020-09-08 | 2020-09-14 | 204.35 | 200.29
0.3.10 | 0.4 |  |  | 0.5 |  | 0.5 | 2020-09-08 | 2020-09-14 | 203.85 | 199.89
0.3.11 | 0.4 |  |  | 0.5 |  | 0.5 | 2020-09-08 | 2020-09-14 | 203.35 | 199.49
0.3.12 | 0.4 |  |  | 0.5 |  | 0.5 | 2020-09-08 | 2020-09-14 | 202.85 | 199.09
0.3.13 | 0.4 |  |  |  | 0.5 | 0.5 | 2020-09-08 | 2020-09-14 | 202.35 | 198.69
0.3.14 | 0.4 |  |  | 0.25 | 0.5 | 0.75 | 2020-09-08 | 2020-09-14 | 201.6 | 198.29
0.3.15 | 0.4 |  |  | 0.25 |  | 0.25 | 2020-09-08 | 2020-09-14 | 201.35 | 197.89
0.4.1 | 0.5 |  | 0.25 | 0.25 |  | 0.5 | 2020-09-08 | 2020-09-15 | 200.85 | 197.39
0.4.2 | 1 |  | 1 |  |  | 1 | 2020-09-08 | 2020-09-15 | 199.85 | 196.39
0.4.3 | 1.5 |  | 1 |  |  | 1 | 2020-09-08 | 2020-09-15 | 198.85 | 194.89
0.5.1 | 1 | 0.2 | 0.75 | 0.15 |  | 1.1 | 2020-09-08 | 2020-09-17 | 197.75 | 193.89
0.5.2 | 2 |  | 1 |  |  | 1 | 2020-09-08 | 2020-09-17 | 196.75 | 191.89
0.5.3 | 1.5 |  | 1 |  |  | 1 | 2020-09-08 | 2020-09-17 | 195.75 | 190.39
0.5.4 | 1 |  | 1 |  |  | 1 | 2020-09-08 | 2020-09-17 | 194.75 | 189.39
0.6.1 | 1 | 0.15 |  |  |  | 0.15 | 2020-09-08 | 2020-09-18 | 194.6 | 188.39
0.6.2 | 1 | 0.5 |  | 0.5 |  | 1 | 2020-09-08 | 2020-09-18 | 193.6 | 187.39
0.6.3 | 0.5 | 0.2 | 0.1 | 0.1 |  | 0.4 | 2020-09-08 | 2020-09-18 | 193.2 | 186.89
0.7.1 | 1 |  |  |  | 1 | 1 | 2020-09-08 | 2020-09-18 | 192.2 | 185.89
0.7.2 | 1 |  |  |  | 1 | 1 | 2020-09-08 | 2020-09-18 | 191.2 | 184.89
0.8.1 | 1 | 1 |  |  |  | 1 | 2020-09-08 | 2020-09-19 | 190.2 | 183.89
0.8.2 | 1 | 1 |  |  |  | 1 | 2020-09-08 | 2020-09-19 | 189.2 | 182.89
0.8.3 | 1 | 0.5 |  |  |  | 0.5 | 2020-09-08 | 2020-09-19 | 188.7 | 181.89
0.9.0 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.4 | 2020-09-08 | 2020-09-19 | 188.3 | 181.49
0.9.1 | 0.2 |  |  | 0.1 | 0.1 | 0.2 | 2020-09-08 | 2020-09-21 | 188.1 | 181.29
0.10.1 | 1.5 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 2020-09-08 | 2020-09-21 | 187.1 | 179.79
0.10.2 | 0.25 |  | 0.25 |  |  | 0.25 | 2020-09-08 | 2020-09-21 | 186.85 | 179.54
0.10.3 | 0.25 |  | 0.25 |  |  | 0.25 | 2020-09-08 | 2020-09-21 | 186.6 | 179.29
0.10.4 | 1.5 | 1 |  | 0.5 |  | 1.5 | 2020-09-08 | 2020-09-22 | 185.1 | 177.79
0.10.5 | 1 | 0.5 |  | 0.5 |  | 1 | 2020-09-08 | 2020-09-22 | 184.1 | 176.79
0.10.6 | 0.5 |  | 0.5 |  |  | 0.5 | 2020-09-08 | 2020-09-22 | 183.6 | 176.29
1.1.1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2020-09-23 | 2020-09-24 | 181.6 | 175.29
1.1.2 | 1 | 1 | 0 | 0 | 0 | 1 | 2020-09-23 | 2020-09-24 | 180.6 | 174.29
1.1.3 | 1 | 0.5 | 0.5 | 0.5 | 0 | 1.5 | 2020-09-23 | 2020-09-24 | 179.1 | 173.29
1.2.1 | 3 | 1 | 1 | 0.5 | 0.5 | 3 | 2020-09-23 | 2020-09-26 | 176.1 | 170.29
1.2.2 | 3 | 1 | 1 | 0.5 | 1 | 3.5 | 2020-09-23 | 2020-09-26 | 172.6 | 167.29
1.2.3 | 3 | 1 | 0 | 1 | 1 | 3 | 2020-09-23 | 2020-09-26 | 169.6 | 164.29
1.3.1 | 1.29 | 0 | 1.25 | 0.25 | 0 | 1.5 | 2020-09-23 | 2020-09-28 | 168.1 | 163
1.3.2 | 1.29 | 0 | 0 | 0.25 | 1.25 | 1.5 | 2020-09-23 | 2020-09-28 | 166.6 | 161.71
1.3.3 | 1.29 | 0 | 0 | 1.25 | 0 | 1.25 | 2020-09-23 | 2020-09-28 | 165.35 | 160.42
1.3.4 | 1.29 | 1.3 | 0 | 0 | 0 | 1.3 | 2020-09-23 | 2020-09-28 | 164.05 | 159.13
1.3.5 | 1.29 | 0 | 1.3 | 0 | 0 | 1.3 | 2020-09-23 | 2020-09-28 | 162.75 | 157.84
1.3.6 | 1.29 | 0 | 0 | 1.3 | 0 | 1.3 | 2020-09-23 | 2020-09-28 | 161.45 | 156.55
1.3.8 | 1.29 | 0 | 0 | 0 | 1.3 | 1.3 | 2020-09-23 | 2020-09-28 | 160.15 | 155.26
1.5.1 | 0.86 | 0.3 | 0.7 | 0 | 0 | 1 | 2020-09-23 | 2020-10-02 | 159.15 | 154.4
1.5.2 | 0.86 | 0 | 0.3 | 0.7 | 0 | 1 | 2020-09-23 | 2020-10-02 | 158.15 | 153.54
1.5.3 | 0.86 | 0 | 0 | 0.3 | 0.7 | 1 | 2020-09-23 | 2020-10-02 | 157.15 | 152.68
1.5.4 | 0.86 | 0.3 | 0.3 | 0.3 | 0.3 | 1.2 | 2020-09-23 | 2020-10-02 | 155.95 | 151.82
1.5.5 | 0.86 | 0.7 | 0.3 | 0 | 0 | 1 | 2020-09-23 | 2020-10-02 | 154.95 | 150.96
1.5.6 | 0.86 | 0.3 | 0.3 | 0.3 | 0 | 0.9 | 2020-09-23 | 2020-10-04 | 154.05 | 150.1
1.5.7 | 0.86 | 0 | 0 | 0.3 | 0.7 | 1 | 2020-09-23 | 2020-10-04 | 153.05 | 149.24
1.7.1 | 1.29 | 0.65 | 0 | 0.65 | 0 | 1.3 | 2020-09-23 | 2020-10-04 | 151.75 | 147.95
1.7.2 | 1.29 | 0.65 | 0.65 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-04 | 150.45 | 146.66
1.7.3 | 1.29 | 0 | 0.7 | 0.7 | 0.7 | 2.1 | 2020-09-23 | 2020-10-04 | 148.35 | 145.37
1.7.4 | 1.29 | 0.65 | 0.65 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-04 | 147.05 | 144.08
1.7.5 | 1.29 | 0 | 0 | 0.65 | 0.65 | 1.3 | 2020-09-23 | 2020-10-04 | 145.75 | 142.79
1.7.6 | 1.29 | 0 | 0 | 0.65 | 0.65 | 1.3 | 2020-09-23 | 2020-10-04 | 144.45 | 141.5
1.7.7 | 1.29 | 0.65 | 0.65 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-04 | 143.15 | 140.21
1.9.1 | 1.29 | 0 | 0 | 0.65 | 0.65 | 1.3 | 2020-09-23 | 2020-10-05 | 141.85 | 138.92
1.9.2 | 1.29 | 0 | 0 | 0 | 1.3 | 1.3 | 2020-09-23 | 2020-10-05 | 140.55 | 137.63
1.9.3 | 1.29 | 1.3 | 0 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-05 | 139.25 | 136.34
1.9.4 | 1.29 | 0 | 1.3 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-05 | 137.95 | 135.05
1.9.5 | 1.29 | 0.65 | 0 | 0 | 0.65 | 1.3 | 2020-09-23 | 2020-10-05 | 136.65 | 133.76
1.9.6 | 1.29 | 0.65 | 0.65 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-05 | 135.35 | 132.47
1.9.7 | 1.29 | 0.65 | 0 | 0 | 0.65 | 1.3 | 2020-09-23 | 2020-10-05 | 134.05 | 131.18
1.10.1 | 1.29 | 0 | 0 | 1.3 | 0 | 1.3 | 2020-09-23 | 2020-10-06 | 132.75 | 129.89
1.10.2 | 1.29 | 0 | 1.3 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-06 | 131.45 | 128.6
1.10.3 | 1.29 | 0 | 0 | 1.3 | 0 | 1.3 | 2020-09-23 | 2020-10-06 | 130.15 | 127.31
1.10.4 | 1.29 | 0 | 0 | 0 | 1.3 | 1.3 | 2020-09-23 | 2020-10-06 | 128.85 | 126.02
1.10.5 | 1.29 | 0 | 0.65 | 0.65 | 0 | 1.3 | 2020-09-23 | 2020-10-06 | 127.55 | 124.73
1.10.6 | 1.29 | 1.3 | 0 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-06 | 126.25 | 123.44
1.10.7 | 1.29 | 0 | 0.65 | 0 | 0.65 | 1.3 | 2020-09-23 | 2020-10-06 | 124.95 | 122.15
1.11.1 | 1.29 | 0 | 0.65 | 0.65 | 0 | 1.3 | 2020-09-23 | 2020-10-07 | 123.65 | 120.86
1.11.2 | 1.29 | 0.65 | 0 | 0 | 0.65 | 1.3 | 2020-09-23 | 2020-10-07 | 122.35 | 119.57
1.11.3 | 1.29 | 0 | 0 | 0.65 | 0.65 | 1.3 | 2020-09-23 | 2020-10-07 | 121.05 | 118.28
1.11.4 | 1.29 | 1.3 | 0 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-07 | 119.75 | 116.99
1.11.5 | 1.29 | 0 | 1.3 | 0 | 0 | 1.3 | 2020-09-23 | 2020-10-07 | 118.45 | 115.7
1.11.6 | 1.29 | 0 | 0 | 0 | 1.3 | 1.3 | 2020-09-23 | 2020-10-07 | 117.15 | 114.41
1.11.7 | 1.29 | 0 | 0.65 | 0.65 | 0 | 1.3 | 2020-09-23 | 2020-10-07 | 115.85 | 113.12
1.14.1 | 0.86 | 0.86 | 0 | 0 | 0 | 0.86 | 2020-09-23 | 2020-10-12 | 114.99 | 112.26
1.14.2 | 0.86 | 0 | 0.86 | 0 | 0 | 0.86 | 2020-09-23 | 2020-10-12 | 114.13 | 111.4
1.14.3 | 0.86 | 0 | 0 | 1 | 0 | 1 | 2020-09-23 | 2020-10-12 | 113.13 | 110.54
1.14.4 | 0.86 | 0 | 0 | 0 | 1 | 1 | 2020-09-23 | 2020-10-12 | 112.13 | 109.68
1.14.5 | 0.86 | 0.9 | 0 | 0 | 0 | 0.9 | 2020-09-23 | 2020-10-12 | 111.23 | 108.82
1.14.6 | 0.86 | 0 | 0 | 0.9 | 0 | 0.9 | 2020-09-23 | 2020-10-13 | 110.33 | 107.96
1.14.7 | 0.86 | 0.86 | 0 | 0 | 0 | 0.86 | 2020-10-15 | 2020-10-13 | 109.47 | 107.1
1.15.1 | 0.9 | 0.5 | 0.5 | 0 | 0 | 1 | 2020-10-15 | 2020-10-13 | 108.47 | 106.2
1.15.2 | 0.9 | 0 | 0 | 0.5 | 0.5 | 1 | 2020-10-15 | 2020-10-13 | 107.47 | 105.3
1.15.3 | 0.9 | 0.45 | 0 | 0 | 0.45 | 0.9 | 2020-10-15 | 2020-10-14 | 106.57 | 104.4
1.15.4 | 0.9 | 0 | 0.45 | 0.5 | 0 | 0.95 | 2020-10-15 | 2020-10-14 | 105.62 | 103.5
1.15.5 | 0.9 | 0 | 0 | 0.5 | 0.45 | 0.95 | 2020-10-15 | 2020-10-14 | 104.67 | 102.6
1.15.6 | 0.9 | 0 | 0 | 0 | 0.9 | 0.9 | 2020-10-15 | 2020-10-14 | 103.77 | 101.7
1.15.7 | 0.9 | 0.45 | 0 | 0 | 0.45 | 0.9 | 2020-10-15 | 2020-10-16 | 102.87 | 100.8
1.15.8 | 0.9 | 0 | 0 | 0.9 | 0 | 0.9 | 2020-10-15 | 2020-10-16 | 101.97 | 99.9
1.15.9 | 0.9 | 0.45 | 0 | 0 | 0.45 | 0.9 | 2020-10-15 | 2020-10-17 | 101.07 | 99
1.15.10 | 0.9 | 0 | 0.9 | 0 | 0 | 0.9 | 2020-10-15 | 2020-10-17 | 100.17 | 98.1
1.16.1 | 1 | 1 | 0 | 0 | 0 | 1 | 2020-10-17 | 2020-10-18 | 99.17 | 97.1
1.16.2 | 1 | 0 | 2 | 0 | 0 | 2 | 2020-10-17 | 2020-10-18 | 97.17 | 96.1
1.16.3 | 1 | 0 | 0 | 1 | 0 | 1 | 2020-10-17 | 2020-10-18 | 96.17 | 95.1
2.1.1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2020-10-27 | 2020-10-27 | 94.17 | 94.1
2.1.2 | 0.5 | 0 | 1 | 0 | 0.25 | 1.25 | 2020-10-27 | 2020-10-28 | 92.92 | 93.6
2.1.3 | 0.4 | 0.5 | 0 | 0.5 | 0.2 | 1.2 | 2020-10-27 | 2020-10-28 | 91.72 | 93.2
2.2.1 | 0.5 | 0.5 | 0.05 | 0.8 | 0.5 | 1.85 | 2020-10-27 | 2020-10-29 | 89.87 | 92.7
2.2.2 | 0.5 | 0 | 0 | 0.8 | 0.2 | 1 | 2020-10-27 | 2020-10-29 | 88.87 | 92.2
2.2.3 | 1 | 0 | 0.5 | 0 | 0.25 | 0.75 | 2020-10-27 | 2020-10-30 | 88.12 | 91.2
2.3.1 | 0.8 | 1 | 0.25 | 0 | 0 | 1.25 | 2020-10-27 | 2020-11-01 | 86.87 | 90.4
2.3.2 | 0.7 | 0.8 | 0 | 1 | 0.05 | 1.85 | 2020-10-27 | 2020-11-01 | 85.02 | 89.7
2.3.3 | 0.8 | 0 | 0.25 | 0 | 0.25 | 0.5 | 2020-10-27 | 2020-11-02 | 84.52 | 88.9
2.3.4 | 0.7 | 0.5 | 0.5 | 0 | 0.5 | 1.5 | 2020-10-27 | 2020-11-02 | 83.02 | 88.2
2.3.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 2020-10-27 | 2020-11-02 | 82.52 | 87.7
2.3.6 | 1 | 0.5 | 1 | 0 | 0.25 | 1.75 | 2020-10-27 | 2020-11-02 | 80.77 | 86.7
2.3.7 | 1 | 1 | 0 | 0 | 0 | 1 | 2020-10-27 | 2020-11-02 | 79.77 | 85.7
2.4.1 | 0.8 | 0.5 | 0.6 | 0 | 0.25 | 1.35 | 2020-10-27 | 2020-11-03 | 78.42 | 84.9
2.4.2 | 0.7 | 1 | 0.5 | 1 | 0 | 2.5 | 2020-10-27 | 2020-11-03 | 75.92 | 84.2
2.4.3 | 0.7 | 0.5 | 0 | 0.5 | 0.5 | 1.5 | 2020-10-27 | 2020-11-04 | 74.42 | 83.5
2.4.4 | 1 | 0 | 0.25 | 0 | 0 | 0.25 | 2020-10-27 | 2020-11-04 | 74.17 | 82.5
2.4.5 | 0.93 | 0 | 1 | 0 | 0.5 | 1.5 | 2020-10-27 | 2020-11-06 | 72.67 | 81.57
2.4.6 | 1 | 0.25 | 0 | 1 | 0 | 1.25 | 2020-10-27 | 2020-11-06 | 71.42 | 80.57
2.4.7 | 0.5 | 1 | 0.25 | 0 | 0.25 | 1.5 | 2020-10-27 | 2020-11-07 | 69.92 | 80.07
2.5.1 | 0.93 | 0.05 | 0 | 0 | 0 | 0.05 | 2020-10-27 | 2020-11-08 | 69.87 | 79.14
2.5.2 | 0.7 | 0 | 0.5 | 1 | 0.5 | 2 | 2020-10-27 | 2020-11-08 | 67.87 | 78.44
2.5.3 | 0.7 | 0.5 | 0.2 | 0 | 0.25 | 0.95 | 2020-10-27 | 2020-11-09 | 66.92 | 77.74
2.5.4 | 0.93 | 0.5 | 0.25 | 0.2 | 0.2 | 1.15 | 2020-10-27 | 2020-11-09 | 65.77 | 76.81
2.5.5 | 0.5 | 0.5 | 0.05 | 0.5 | 0.5 | 1.55 | 2020-10-27 | 2020-11-09 | 64.22 | 76.31
2.5.6 | 1 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-10 | 64.22 | 75.31
2.5.7 | 1 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-10 | 64.22 | 74.31
2.6.1 | 0.7 | 0.25 | 0.25 | 1 | 0 | 1.5 | 2020-10-27 | 2020-11-11 | 62.72 | 73.61
2.6.2 | 0.8 | 0.05 | 0 | 0.5 | 0.05 | 0.6 | 2020-10-27 | 2020-11-11 | 62.12 | 72.81
2.6.3 | 0.7 | 0 | 0.4 | 0.25 | 0.5 | 1.15 | 2020-10-27 | 2020-11-11 | 60.97 | 72.11
2.6.4 | 1 | 1 | 0.5 | 0 | 0.05 | 1.55 | 2020-10-27 | 2020-11-11 | 59.42 | 71.11
2.6.5 | 0.93 | 0.5 | 0 | 0.25 | 0 | 0.75 | 2020-10-27 | 2020-11-11 | 58.67 | 70.18
2.6.6 | 0.93 | 0 | 0 | 0.05 | 0 | 0.05 | 2020-10-27 | 2020-11-11 | 58.62 | 69.25
2.6.7 | 0.8 | 0 | 0.5 | 1 | 0.8 | 2.3 | 2020-10-27 | 2020-11-11 | 56.32 | 68.45
2.7.1 | 0.8 | 0 | 0.25 | 0 | 0.2 | 0.45 | 2020-10-27 | 2020-11-12 | 55.87 | 67.65
2.7.2 | 0.7 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-12 | 55.87 | 66.95
2.7.3 | 0.7 | 0.25 | 0 | 0.25 | 0 | 0.5 | 2020-10-27 | 2020-11-12 | 55.37 | 66.25
2.7.4 | 0.93 | 0 | 0.4 | 0 | 0.25 | 0.65 | 2020-10-27 | 2020-11-12 | 54.72 | 65.32
2.7.5 | 0.5 | 0 | 0.05 | 0 | 0 | 0.05 | 2020-10-27 | 2020-11-12 | 54.67 | 64.82
2.7.6 | 0.7 | 0.25 | 0 | 0.05 | 0 | 0.3 | 2020-10-27 | 2020-11-12 | 54.37 | 64.12
2.7.7 | 0.67 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-12 | 54.37 | 63.45
2.8.1 | 1 | 0 | 0.25 | 0 | 0.25 | 0.5 | 2020-10-27 | 2020-11-13 | 53.87 | 62.45
2.8.2 | 0.5 | 0 | 0 | 0.25 | 0 | 0.25 | 2020-10-27 | 2020-11-13 | 53.62 | 61.95
2.8.3 | 0.93 | 0.5 | 0 | 0 | 0 | 0.5 | 2020-10-27 | 2020-11-13 | 53.12 | 61.02
2.8.4 | 1 | 0.25 | 0 | 0.25 | 0 | 0.5 | 2020-10-27 | 2020-11-14 | 52.62 | 60.02
2.8.5 | 0.5 | 0 | 0 | 0 | 0.2 | 0.2 | 2020-10-27 | 2020-11-14 | 52.42 | 59.52
2.8.6 | 0.75 | 0.25 | 0.25 | 0 | 0 | 0.5 | 2020-10-27 | 2020-11-14 | 51.92 | 58.77
2.8.7 | 0.93 | 0 | 0 | 0 | 0.25 | 0.25 | 2020-10-27 | 2020-11-14 | 51.67 | 57.84
2.9.1 | 0.7 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-15 | 51.67 | 57.14
2.9.2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-15 | 51.67 | 56.64
2.9.3 | 0.7 | 0.05 | 0 | 0.05 | 0.05 | 0.15 | 2020-10-27 | 2020-11-15 | 51.52 | 55.94
2.9.4 | 1 | 0 | 0.25 | 0 | 0 | 0.25 | 2020-10-27 | 2020-11-16 | 51.27 | 54.94
2.9.5 | 1 | 0 | 0 | 0.25 | 0 | 0.25 | 2020-10-27 | 2020-11-16 | 51.02 | 53.94
2.9.6 | 0.5 | 0 | 0 | 0 | 0.05 | 0.05 | 2020-10-27 | 2020-11-16 | 50.97 | 53.44
2.9.7 | 1 | 0.05 | 0.25 | 0.25 | 0 | 0.55 | 2020-10-27 | 2020-11-16 | 50.42 | 52.44
2.10.1 | 0.9 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-17 | 50.42 | 51.54
2.10.2 | 0.9 | 0.25 | 0 | 0.25 | 0 | 0.5 | 2020-10-27 | 2020-11-17 | 49.92 | 50.64
2.10.3 | 0.9 | 0.2 | 0 | 0.2 | 0 | 0.4 | 2020-10-27 | 2020-11-17 | 49.52 | 49.74
2.10.4 | 1 | 0 | 0.25 | 0 | 0.25 | 0.5 | 2020-10-27 | 2020-11-17 | 49.02 | 48.74
2.10.5 | 0.5 | 0.05 | 0 | 0.05 | 0.25 | 0.35 | 2020-10-27 | 2020-11-18 | 48.67 | 48.24
2.10.6 | 1 | 0 | 0.25 | 0.25 | 0 | 0.5 | 2020-10-27 | 2020-11-18 | 48.17 | 47.24
2.10.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 2020-10-27 | 2020-11-18 | 48.17 | 46.54
2.10.8 | 0.93 | 0 | 0 | 0 | 0.5 | 0.5 | 2020-10-27 | 2020-11-18 | 47.67 | 45.61
2.10.9 | 0.7 | 0.25 | 0 | 0 | 0 | 0.25 | 2020-10-27 | 2020-11-18 | 47.42 | 44.91
2.10.10 | 0.7 | 0 | 0.25 | 0 | 0.8 | 1.05 | 2020-10-27 | 2020-11-18 | 46.37 | 44.21
2.11.1 | 0.5 | 0 | 0.5 | 0 | 0 | 0.5 | 2020-10-27 | 2020-11-19 | 45.87 | 43.71
2.11.2 | 1 | 0 | 0 | 2 | 0 | 2 | 2020-10-27 | 2020-11-19 | 43.87 | 42.71
2.11.3 | 1 | 0.25 | 0 | 0.25 | 0.25 | 0.75 | 2020-10-27 | 2020-11-19 | 43.12 | 41.71
3.1.1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2020-11-30 | 2020-11-30 | 41.12 | 40.71
3.1.2 | 0.5 | 0 | 1 | 0 | 0.25 | 1.25 | 2020-11-30 | 2020-11-30 | 39.87 | 40.21
3.1.3 | 0.4 | 0.5 | 0 | 0.5 | 0.2 | 1.2 | 2020-11-30 | 2020-11-30 | 38.67 | 39.81
3.2.1 | 0.5 | 0.5 | 0.05 | 0.8 | 0.5 | 1.85 | 2020-11-30 | 2020-12-01 | 36.82 | 39.31
3.2.2 | 0.5 | 0 | 0 | 0.8 | 0.2 | 1 | 2020-11-30 | 2020-12-01 | 35.82 | 38.81
3.2.3 | 1 | 0 | 0.5 | 0 | 0.25 | 0.75 | 2020-11-30 | 2020-12-01 | 35.07 | 37.81
3.3.1 | 0.7 | 0.25 | 0.25 | 1 | 0 | 1.5 | 2020-11-30 | 2020-12-01 | 33.57 | 37.11
3.3.2 | 0.8 | 0.05 | 0 | 0.5 | 0.05 | 0.6 | 2020-11-30 | 2020-12-01 | 32.97 | 36.31
3.3.3 | 0.7 | 0 | 0.4 | 0.25 | 0.5 | 1.15 | 2020-11-30 | 2020-12-04 | 31.82 | 35.61
3.3.4 | 1 | 1 | 0.5 | 0 | 0.05 | 1.55 | 2020-11-30 | 2020-12-04 | 30.27 | 34.61
3.3.5 | 0.93 | 0.5 | 0 | 0.25 | 0 | 0.75 | 2020-11-30 | 2020-12-04 | 29.52 | 33.68
3.3.6 | 0.93 | 0 | 0 | 0.05 | 0 | 0.05 | 2020-11-30 | 2020-12-04 | 29.47 | 32.75
3.3.7 | 0.8 | 0 | 0.5 | 1 | 0.8 | 2.3 | 2020-11-30 | 2020-12-04 | 27.17 | 31.95
3.4.1 | 0.8 | 0 | 0.25 | 0 | 0.2 | 0.45 | 2020-11-30 | 2020-12-04 | 26.72 | 31.15
3.4.2 | 0.7 | 0 | 0.23 | 0 | 0.3 | 0.53 | 2020-11-30 | 2020-12-04 | 26.19 | 30.45
3.4.3 | 0.7 | 0.25 | 0 | 0.25 | 0 | 0.5 | 2020-11-30 | 2020-12-04 | 25.69 | 29.75
3.4.4 | 0.93 | 0 | 0.4 | 0 | 0.25 | 0.65 | 2020-11-30 | 2020-12-07 | 25.04 | 28.82
3.4.5 | 0.5 | 0 | 0.05 | 0 | 0 | 0.05 | 2020-11-30 | 2020-12-07 | 24.99 | 28.32
3.4.6 | 0.7 | 0.5 | 0 | 0.05 | 0 | 0.55 | 2020-11-30 | 2020-12-07 | 24.44 | 27.62
3.4.7 | 0.67 | 0 | 0.3 | 0 | 0.2 | 0.5 | 2020-11-30 | 2020-12-07 | 23.94 | 26.95
3.5.1 | 1 | 0 | 0.25 | 0 | 0.25 | 0.5 | 2020-11-30 | 2020-12-07 | 23.44 | 25.95
3.5.2 | 0.5 | 0 | 0 | 0.25 | 0 | 0.25 | 2020-11-30 | 2020-12-07 | 23.19 | 25.45
3.5.3 | 0.93 | 0.5 | 0 | 0 | 0 | 0.5 | 2020-11-30 | 2020-12-07 | 22.69 | 24.52
3.5.4 | 1 | 0.25 | 0 | 0.25 | 0 | 0.5 | 2020-11-30 | 2020-12-07 | 22.19 | 23.52
3.5.5 | 0.5 | 0 | 0 | 0 | 0.2 | 0.2 | 2020-11-30 | 2020-12-10 | 21.99 | 23.02
3.5.6 | 0.75 | 0.3 | 0.25 | 0 | 0 | 0.55 | 2020-11-30 | 2020-12-10 | 21.44 | 22.27
3.5.7 | 0.93 | 0 | 0 | 0 | 0.25 | 0.25 | 2020-11-30 | 2020-12-10 | 21.19 | 21.34
3.6.1 | 0.7 | 0 | 0 | 0.3 | 0.15 | 0.45 | 2020-11-30 | 2020-12-10 | 20.74 | 20.64
3.6.2 | 0.5 | 0.25 | 0 | 0 | 0 | 0.25 | 2020-11-30 | 2020-12-10 | 20.49 | 20.14
3.6.3 | 0.7 | 0.2 | 0 | 0.05 | 0.05 | 0.3 | 2020-11-30 | 2020-12-13 | 20.19 | 19.44
3.6.4 | 1 | 0 | 0.25 | 0 | 0 | 0.25 | 2020-11-30 | 2020-12-13 | 19.94 | 18.44
3.6.5 | 1 | 0.3 | 0 | 0.25 | 0 | 0.55 | 2020-11-30 | 2020-12-13 | 19.39 | 17.44
3.6.6 | 0.5 | 0 | 0 | 0 | 0.05 | 0.05 | 2020-11-30 | 2020-12-13 | 19.34 | 16.94
3.6.7 | 1 | 0.05 | 0.25 | 0.25 | 0 | 0.55 | 2020-11-30 | 2020-12-13 | 18.79 | 15.94
3.7.1 | 0.88 | 0.4 | 0.25 | 0.3 | 0.3 | 1.25 | 2020-11-30 | 2020-12-13 | 17.54 | 15.06
3.7.2 | 0.6 | 0.05 | 0.05 | 0.05 | 0.05 | 0.2 | 2020-11-30 | 2020-12-13 | 17.34 | 14.46
3.7.3 | 0.78 | 1 | 1 | 0 | 1 | 3 | 2020-11-30 | 2020-12-13 | 14.34 | 13.68
3.7.4 | 0.5 | 0.05 | 0.25 | 0.2 | 0.25 | 0.75 | 2020-11-30 | 2020-12-13 | 13.59 | 13.18
3.7.5 | 1 | 0.05 | 0.22 | 0.2 | 0.22 | 0.69 | 2020-11-30 | 2020-12-13 | 12.9 | 12.18
3.7.6 | 0.55 | 0.05 | 0.3 | 0 | 0.3 | 0.65 | 2020-11-30 | 2020-12-13 | 12.25 | 11.63
3.7.7 | 0.9 | 0.05 | 1 | 0.2 | 1 | 2.25 | 2020-11-30 | 2020-12-13 | 10 | 10.73
3.8.1 | 0.9 | 1 | 0 | 0 | 0 | 1 | 2020-11-30 | 2020-12-15 | 9 | 9.83
3.8.2 | 0.9 | 0.25 | 0 | 0.25 | 0 | 0.5 | 2020-11-30 | 2020-12-15 | 8.5 | 8.93 | Actual Hours | Estimated Hours
3.8.3 | 0.9 | 0.2 | 0 | 0.2 | 0 | 0.4 | 2020-11-30 | 2020-12-15 | 8.1 | 8.03 | 39.8 | 38.6
3.8.4 | 1 | 0 | 0.25 | 0 | 0.25 | 0.5 | 2020-11-30 | 2020-12-15 | 7.6 | 7.03 | 87.43 | 81.19
3.8.5 | 0.5 | 0.05 | 0 | 0.05 | 0.25 | 0.35 | 2020-11-30 | 2020-12-15 | 7.25 | 6.53 | 53.05 | 53.39
3.8.6 | 1 | 0 | 0.25 | 0.25 | 0 | 0.5 | 2020-11-30 | 2020-12-15 | 6.75 | 5.53 | 43.12 | 41.71
3.8.7 | 0.7 | 1 | 0.2 | 0 | 0 | 1.2 | 2020-11-30 | 2020-12-15 | 5.55 | 4.83 | 223.4 | 214.89
3.8.8 | 0.93 | 0.5 | 0 | 0 | 0.5 | 1 | 2020-11-30 | 2020-12-16 | 4.55 | 3.9
3.8.9 | 0.7 | 0.25 | 0 | 0 | 0 | 0.25 | 2020-11-30 | 2020-12-16 | 4.3 | 3.2
3.8.10 | 0.7 | 0 | 0.25 | 0 | 0.8 | 1.05 | 2020-11-30 | 2020-12-16 | 3.25 | 2.5
3.9.1 | 0.5 | 0 | 0.5 | 0 | 0 | 0.5 | 2020-11-30 | 2020-12-16 | 2.75 | 2
3.9.2 | 1 | 0 | 0 | 2 | 0 | 2 | 2020-11-30 | 2020-12-16 | 0.75 | 1
3.9.3 | 1 | 0.25 | 0 | 0.25 | 0.25 | 0.75 | 2020-11-30 | 2020-12-16 | 0 | 0

## EPICS
Sprint | SR# | EPIC Description
0 | 1 | Requirement Gathering. Convert it to stories and prioritize.
| 3 | Create Mock-ups of all integral screens
| 4 | Create a Use-Case Diagram of the product
| 5 | Create Data Model based on mock ups
| 6 | Use Trello Board to identify and allocate tasks for upcoming Sprint
| 7 | Come up with a logo for ecommerce application
| 8 | Create class diagrams based on Data Model
| 9 | Create detailed project release plan for all sprints
| 10 | Set up Integration environment and common code repository
| 11 | Create Product Demonstration for Sprint 0
1 | 13 | Develop User Interface for Home Page
| 14 | Develop User Interface for Administrator and add their privileges
| 15 | Create Login Page for Admin and Customer
| 16 | As an admin, I want to add new user
| 17 | As an admin, I want to modify/delete users and their details
| 18 | As an admin, I want to add new product
| 19 | As an admin, I want to modify/delete the products and their details
| 20 | As an admin, I want access to viewing all products and all users
| 21 | As a customer, I want to register myself as a new user
| 22 | As a customer, I want to add products to the shopping cart
| 23 | As a customer, I want to modify/delete the products in the cart
| 24 | As a customer I want to view the Products based on categorys
| 25 | As a customer, I want to view the product detail page
| 26 | As a customer, I want to view Product detail page
| 27 | As a customer I want to view the Products based on categorys
| 28 | As a customer, I want to view the product detail page
| 29 | As an admin, I want to add categories
| 30 | As an admin, I want to modify/delete categories
| 31 | As an admin, I want to categorize products based on categories
| 32 | As a customer, I want to change my password after login
| 33 | As a customer, I want to reset my password before login
| 34 | As a customer, I want to add shipping address
| 35 | Integration of Google API
| 36 | Integration of Geo location API
| 37 | Integration of currency conversion API
2 | 38 | As a customer, I want to view the About us
| 39 | As an admin, I want to add/modify/delete orders
| 40 | As an admin, I want to add/modify/delete orders items
| 41 | As an admin, I want to add/modify/delete shipping address
| 42 | As a customer, I want to make the payment
| 43 | Integration of twilio API for sending SMS notification for the order placed
| 44 | Integration of Mail trap for sending email notification
| 45 | Integration of PayPal API with the application
| 46 | Integration of Custom Api
| 47 | Integration of currency converter API
| 48 | As a customer, I want to view the details of the purchased products
| 49 | As a customer, I want to view the order summary of the purchased products
| 50 | As a customer, I want to view the contact us page
| 51 | Sprint 2 Product Demonstration